## Sheet1
S.No | Task Description | Owner | Target Date | Comments
1 | Code Sanitation
1.1 | Request oktarack to provide prod/live files | Niladri
1.2 | Create main branch and upload the prod/live files | Niladri
1.3 | Developer will checkout the code from this main branch and sanitize | Biru |  | This activity may be performed module by module
1.4 | Developer commits the code back to the main code line | Biru |  | This activity may be performed module by module
1.5 | SCM engineer will checkout this commited code from step 1.4 on his machine | Niladri
1.6 | SCM engineer wil try to compile the code on his machine | Niladri |  | For any build failures SCM and Dev will work together and resolve
2 | Test Build Sanitization
2.1 | SCM engineer will create war files for Test deployment | Niladri
2.2 | SCM engineer will deploy the above war files on test machine | Niladri |  | For any deployment failures SCM and Dev will work together and resolve
2.3 | Test engineer will test this deployed war files and certify | Testing Team |  | For any Test failures Testers and Dev will work together and resolve
3 | UAT Build Sanitization
2.1 | SCM engineer will create war files for UAT deployment | Niladri
2.2 | SCM engineer will email oktrack for deploying the above war files on UAT machine | Niladri |  | For any deployment failures SCM, oktrack and Dev will work together and resolve
2.3 | Test engineer will test this deployed war files and certify | Testing Team |  | For any Test failures Testers and Dev will work together and resolve
4 | Branching
4.1 | SCM engineer will create a branch for merging any prod changes that happened during the above activity period. | Niladri
4.2 | Dev merges back the changes to the above branch created in step 4.1 | Biru